## Sheet1
Fixit Meeting TimeTable
Team Members
Number | Date | Start Time | End Time | Kranthi | Mrudula | saboor | sapna | Issue | Comments
1 | 2015-09-01 | 19:00 | 20:00 | Y | Y | Y | Y | what is project. who are team mates | Get to know project and team mates
2 | 2015-09-03 | 20:00 | 21:00 | Y | Y | Y | Y | Deciding Project Preferences,decided what type of communication media can be used. | decided as 5 ,1,2,3,4 communication via whats app
3 | 2015-09-04 | 8:00AM | 8:45AM | Y | Y | Y | Y | meeting with Dr.wutrich regarding requirements | Clarity on requirement to be developed
4 | 2015-09-07 | 21:00 | 22:00 | Y | Y | Y | Y | Requirement Draft review | reviewed the draft document and clarified the requirements to be developed with team members
5 | 2015-09-08 | 19:30 | 21:30 | Y | Y | Y | Y | Discussion on rough designs of requirements, and test cases. Requirement draft submission. | Created rough designs and database tables.
6 | 2015-09-10 | 8:15 | 8:50 | Y | Y | Y | Y | Meeting with Dr.wutrich regarding rough screen designs for clarity. | Clarified some doubts with ms. Wutrich .
7 | 2015-09-11 | 11:45 | 12:30 | Y | Y | Y | Y | Meeting in Lab for reviewing the requirement draft changes. | Corrections and design were done.
8 | 2015-09-15 | 20:30 | 21:30 | Y | Y | Y | Y | Project plan discussion | Decided the and assigned task for preparing project plan.
9 | 2015-09-18 | 8:10 | 9:00 | Y | Y | Y | Y | Meeting with Ms. Wutrich for submission of the finalized requirements. | Changed were identified and project plan document rewived and changed made.
10 | 2015-09-21 | 20:45 | 21:30 | Y | Y | Y | Y | Review of Final requirement submission. | Ms. Wutrich and other changes were identified and discussed.
11 | 2015-09-24 | 20:30 | 21:30 | Y | Y | Y | Y | Project plan review discussion | Discussed and verified changes in Ghant chart and reports.
12 | 2015-09-29 | 20:30 | 21:30 | Y | Y | Y | Y | Interface designs and Project presentation | assigned work to team members and decided the designs , topic included.
13 | 2015-10-03 | 7:00PM | 21:00 | Y | Y | Y | Y | Presentation PPt | Review and changes made to ppt.
14 | 2015-10-06 | 20:30 | 21:30 | Y | Y | Y | Y | Interface design | review on the doc and screens data.
15 | 2015-10-08 | 20:00 | 22:00 | Y | Y | Y | Y | finalizing the ppt | worked together to complete and make final changes to ppt.
16 | 2015-10-13 | 20:00 | 20:30 | Y | Y | Y | Y | Objective grading sheet | review and changes made to tasks.
17 | 2015-10-15 | 20:30 | 22:00 | Y | Y | Y | Y | user manual | discussed and worked on the user manual document by all members.
18 | 2015-10-20 | 19:30 | 22:00 | Y | Y | Y | Y | Uml diagram and grading sheets discussion. | Helped each other creating diagrams
19 | 2015-10-22 | 20:00 | 21:45 | Y | Y | Y | Y | coding and implementation | started working on implementation. Discussion on classes, tables, installations and interface fields.
20 | 2015-10-27 | 10:30 | 23:30 | Y | Y | Y | Y | sql problems | worked on sql compatibility with miscrosoft visual studio installation issues.
21 | 2015-11-04 | 20:00 | 21:50 | Y | Y | Y | Y | Test plan and test cases | Discussed what need to be added how to write the test cases.
22 | 2015-11-10 | 20:00 | 21:30 | Y | Y | Y | Y | Installation and setup . | Problem discussion on installation issues, and installation on other machines.
23 | 2015-11-17 | 20:00 | 21:30 | Y | Y | Y | Y | Implementaiton completion | Discussed the implementation and changes to it.
24 | 2015-11-19 | 20:00 | 22:00 | Y | Y | Y | Y | Issues faced after implementation. | errors and validations and testing discussion.
25 | 2015-11-24 | 19:30 | 23:00 | Y | Y | Y | Y | Testing. | Helped each other with testing and writing test cases.
26 | 2015-11-26 | 20:00 | 21:30 | Y | Y | Y | Y | Final PPT | Discussion on report with changes to be made.
27 | 2015-11-30 | 19:00 | 21:45 | Y | Y | Y | Y | Resolving testing issues | Worked on testing and testing issues .
Y: Attended
N: Not Attended